## Issue Tracker
ISSUE TRACKER
ISSUE# | DATE OPENED | PRIORITY | ISSUE DESCRIPTION | INITIAL ANALYSIS | ASSIGNED | STATUS | RESOLUTION | DATE CLOSED | Prorities:-
1 | 2017-03-24 | 3 | Some feeds have the article title and read more link in the wrong order. See the SKY news feed for an example. | This is because of the way the code loops through each xml item searching for a match in mng_feed.php |  | Not Started |  |  | 1 = Critical - nun-functions core element - cannot go live with this defect
2 | 2014-03-24 | 3 | Some feeds have pixelated thumbs on the articles - see Sky News as an example | Likely needs a simple css change |  | Not Started |  |  | 2 = Major - core function severly affected although it may technically work
3 | 2017-03-24 | 2 | Some feeds do not contain an article thumb so currently the code is outputting "undefined" | Add an "undefined" check and use place holder text instead. Mng-feed.php |  | Not Started |  |  | 3 = Minor defect - core functionality works partially but could be improved
4 = Cosmetic or allowable defect. Functionality works fine but be refined