## Issue Tracker
ISSUE TRACKER
ISSUE# | DATE OPENED | PRIORITY | ISSUE DESCRIPTION | INITIAL ANALYSIS | ASSIGNED | STATUS | RESOLUTION | DATE CLOSED | Prorities:-
1 | 2017-03-24 | 3 | Some feeds have the article title and read more link in the wrong order. See the SKY news feed for an example. | This is because of the way the code loops through each xml item searching for a match in mng_feed.php | Rob Sims | Completed | amended comments.php | 2017-03-24 | 1 = Critical - nun-functions core element - cannot go live with this defect
2 | 2014-03-24 | 3 | Some feeds have pixelated thumbs on the articles - see Sky News as an example | Likely needs a simple css change | Rob Sims | Completed | amended comments.php | 2017-03-24 | 2 = Major - core function severly affected although it may technically work
3 | 2017-03-24 | 2 | Some feeds do not contain an article thumb so currently the code is outputting "undefined" | Add an "undefined" check and use place holder text instead. Mng-feed.php | Rob Sims | Completed | amended comments.php | 2017-03-24 | 3 = Minor defect - core functionality works partially but could be improved
4 | 2017-03-28 | 2 | Can view other peoples subscriptions by editing url directly (i.e. putting in a different userid). | Reconmend adding something like if ($_SESSION[userid] != $_GET[userid]) check on mysubscription.php | Rob Sims |  |  |  | 4 = Cosmetic or allowable defect. Functionality works fine but be refined
5 | 2017-03-28 | 3 | Userid superflous for feeds.php and comments.php now we have a separate My Subscriptions page. | Show all feeds to any user that is logged in. | Rob Sims
6 | 2017-03-28 | 3 | Logo is not totally responsive | Check all Media Query breakpoints | Derrick
7 | 2017-07-28 | 4 | Feed thumbs are not responsive | Make responsive through feeds.php and css - see comments'php for similar approach. | Rob Sims